## Sheet1
Sr. No. | Task Name | Description | Progress Status | Start Date | End Date
1 | Download and load dataset | Step 1-Download the dataset (https://www.kaggle.com/datasets/kamilpytlak/personal-key-indicators-of-heart-disease) from kaggle Step 2- Load the data set to the s3 bucket (flatbucket6) | Completed | 2022-03-22 | 2022-03-22
2 | Database creation | Create a database SF_Project | Completed | 2022-03-22 | 2022-03-22
3 | Schema creation | Create a schema ITR_RDS/ITE_Landing | Completed | 2022-03-22 | 2022-03-22
4 | Datamart schema creation | Create a datamart schema - ITR_DIS | Completed | 2022-03-23 | 2022-03-23
5 | Table creation | Create a table HEART_DISEASE as per data set | Completed | 2022-03-23 | 2022-03-23
6 | External stage creation | Create external stage MY_EXT_STAGE for loading the data structure | Completed | 2022-03-23 | 2022-03-23
7 | Snowpipe creation | Create Snowpipe SNOWPIPE1 for auto ingesting data from S3 bucket (bucket name) | Completed | 2022-03-23 | 2022-03-23
8 | Stream creation | Create stream HEART_CHECK on table HEART_DISEASE | Completed | 2022-03-24 | 2022-03-24
9 | SCD creation | Perform SCD 2 operation on consumer table (HEART_DISEASE_TGT) | Completed | 2022-03-24 | 2022-03-24
10 | Task creation | Automate data load from snowpipe to consumer table HEART_TASK on everyday at 12 pm | Completed | 2022-03-24 | 2022-03-24
11 | Data Analysis | 1. which gender have majority heart attack 2.which combination of physical and mental health causes stroke 3.GenHealth wise average BMI of people 4.Average age of people having problem in walking 5.Average BMI of people having Skin Cancer 6. Possibilities/Percentage of people having both Heart Diseases stroke and Skin Cancer | Completed | 2022-03-24 | 2022-03-24